Still Becoming Launch Activation Runbook
Updated: 2026-06-11
Current Status
Kindle eBook: submitted to KDP review on 2026-06-09. KDP says review can take up to 72 hours.
Paperback: final interior PDF and GetCovers full-wrap PDF are complete, uploaded, and re-previewed in KDP. Paperback proof has been ordered; expected delivery to John is 2026-06-13.
Hardcover: added as a non-critical-path KDP case-laminate extension with a 2026-06-14 target; requires separate hardcover ISBN, KDP hardcover template, separate hardcover cover PDF, preview, and proof.
Website: live at https://stillbecomingtools.com with tools, Starter Kit, daily/weekly signup, consulting/speaking forms, Kit routing, Gmail notification, and Google Sheets lead repository.
App: App Store package uploaded/accepted for processing. TestFlight/device UAT remains the gate before App Review submission.
Launch Rule
Do not start paid book ads until the Amazon listing URL is live and the website book CTA has been updated. Until then, use organic posts and Starter Kit/list-building CTAs.
Activation Timeline
	Trigger
	Action
	Owner
	Status

	Now
	Keep website, tools, Starter Kit, consulting/speaking, and newsletter paths live.
	Codex
	Ready

	Kindle listing live
	Capture Amazon URL, update website book CTA, update email/social copy placeholders.
	Codex
	Waiting on KDP

	Kindle listing live
	Send Launch Email 1 and publish Day 15 launch post.
	John/Codex
	Needs approval/send

	24-48 hours after Kindle live
	Post tool walkthrough and sample chapter CTA; start small lead-magnet ad test only if link paths are clean.
	John/Codex
	Staged

	GetCovers final wrap received
	Upload paperback interior/cover, enter ISBN/imprint, run KDP print preview.
	John/Codex
	Complete

	Paperback preview passed
	Order physical proof.
	John/Codex
	Complete; proof delivery expected 2026-06-13

	Proof approved
	Announce paperback availability and consider Amazon Ads.
	John/Codex
	Waiting on physical proof review

	Paperback files stable
	Stage KDP hardcover setup, enter separate hardcover ISBN, generate hardcover template, and request case-laminate cover from GetCovers.
	John/Codex
	Target 2026-06-14

	TestFlight available
	Run device UAT and submit App Review only after John approval.
	John/Codex
	Waiting on ASC



Email Sequence
	Email
	Timing
	Subject
	CTA
	Gate

	1
	Kindle live day
	You are not finished
	Buy Kindle / get Starter Kit
	Needs Amazon URL

	2
	+1 day
	What carries you through transition
	Foundation Inventory
	Ready

	3
	+3 days
	Stabilize before you reinvent
	Use the scorecard
	Ready

	4
	+5 days
	Ownership is the door back
	Use the Ownership Ladder
	Ready

	5
	+7 days
	The three questions reinvention asks
	Use the Reinvention Intersection
	Ready

	6
	+10 days
	AI is a strategic partner
	Use the AI ladder
	Ready

	7
	+14 days
	The work after the book
	Book / consulting / speaking
	Needs live links



Organic Content
	Day
	Theme
	Primary CTA

	1
	Kindle launch / You are not finished
	Amazon Kindle + Starter Kit

	2
	Foundation Inventory
	Starter Kit

	3
	Compliance is not commitment
	Tools

	4
	AI as strategic partner
	AI ladder

	5
	Stabilize first
	Scorecard

	6
	Ownership ladder
	Tools

	7
	Title is not identity
	Starter Kit

	8
	Three rings / reinvention intersection
	Tools

	9
	Grief is not an event
	Newsletter

	10
	Speaking/workshop positioning
	Speaking inquiry

	11
	Tool walkthrough video
	Tools

	12
	Sample chapter
	Starter Kit

	13
	Reader/reviewer feedback ask
	Book link

	14
	Launch recap / next chapter
	Website



$500 Spend Guardrails
	Channel
	Cap
	Start condition
	Stop condition

	Meta lead magnet test
	$150
	Starter Kit and Kit delivery verified
	Pause if cost per subscriber is above $6 after $60 spend

	LinkedIn boost
	$75
	An organic post shows above-average engagement
	Pause if click-through is below 0.8% after $40 spend

	Amazon Ads
	$100
	Amazon listing is live and detail page looks clean
	Pause if no sales after $50 spend or CPC is materially above category economics

	Creative/tool screenshots
	$75
	Use only if needed for clean ad or social visuals
	Spend only on reusable templates/assets

	Reserve
	$100
	Hold for the channel that shows traction
	Do not spend until one channel has evidence



Do not exceed $500 without explicit John approval. Do not scale any channel until the landing page, email capture, book CTA, and at least three creatives have been tested.
Approval Gates
John approves the first launch email before send.
John approves any paid spend before activation.
John approves final paperback proof before paperback public launch.
John approves TestFlight/App Review submission after device UAT.
Immediate Next Actions
Wait for KDP Kindle review result and live Amazon URL.
Wait for paperback proof delivery and physical review on or around 2026-06-13.
Keep website project files and tracking current.
Stage first launch email/social post with live-link placeholders.
Update website CTA and UAT script when the Amazon URL exists.
Continue TestFlight/device UAT and hardcover ISBN/setup prep when account access is available.
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