Still Becoming Launch Activation Runbook

Updated: 2026-06-11

# Current Status

Kindle eBook: submitted to KDP review on 2026-06-09. KDP says review can take up to 72 hours.

Paperback: final interior PDF and GetCovers full-wrap PDF are complete, uploaded, and re-previewed in KDP. Paperback proof has been ordered; expected delivery to John is 2026-06-13.

Hardcover: added as a non-critical-path KDP case-laminate extension with a 2026-06-14 target; requires separate hardcover ISBN, KDP hardcover template, separate hardcover cover PDF, preview, and proof.

Website: live at https://stillbecomingtools.com with tools, Starter Kit, daily/weekly signup, consulting/speaking forms, Kit routing, Gmail notification, and Google Sheets lead repository.

App: App Store package uploaded/accepted for processing. TestFlight/device UAT remains the gate before App Review submission.

# Launch Rule

Do not start paid book ads until the Amazon listing URL is live and the website book CTA has been updated. Until then, use organic posts and Starter Kit/list-building CTAs.

# Activation Timeline

| Trigger | Action | Owner | Status |
| --- | --- | --- | --- |
| Now | Keep website, tools, Starter Kit, consulting/speaking, and newsletter paths live. | Codex | Ready |
| Kindle listing live | Capture Amazon URL, update website book CTA, update email/social copy placeholders. | Codex | Waiting on KDP |
| Kindle listing live | Send Launch Email 1 and publish Day 15 launch post. | John/Codex | Needs approval/send |
| 24-48 hours after Kindle live | Post tool walkthrough and sample chapter CTA; start small lead-magnet ad test only if link paths are clean. | John/Codex | Staged |
| GetCovers final wrap received | Upload paperback interior/cover, enter ISBN/imprint, run KDP print preview. | John/Codex | Complete |
| Paperback preview passed | Order physical proof. | John/Codex | Complete; proof delivery expected 2026-06-13 |
| Proof approved | Announce paperback availability and consider Amazon Ads. | John/Codex | Waiting on physical proof review |
| Paperback files stable | Stage KDP hardcover setup, enter separate hardcover ISBN, generate hardcover template, and request case-laminate cover from GetCovers. | John/Codex | Target 2026-06-14 |
| TestFlight available | Run device UAT and submit App Review only after John approval. | John/Codex | Waiting on ASC |

# Email Sequence

| Email | Timing | Subject | CTA | Gate |
| --- | --- | --- | --- | --- |
| 1 | Kindle live day | You are not finished | Buy Kindle / get Starter Kit | Needs Amazon URL |
| 2 | +1 day | What carries you through transition | Foundation Inventory | Ready |
| 3 | +3 days | Stabilize before you reinvent | Use the scorecard | Ready |
| 4 | +5 days | Ownership is the door back | Use the Ownership Ladder | Ready |
| 5 | +7 days | The three questions reinvention asks | Use the Reinvention Intersection | Ready |
| 6 | +10 days | AI is a strategic partner | Use the AI ladder | Ready |
| 7 | +14 days | The work after the book | Book / consulting / speaking | Needs live links |

# Organic Content

| Day | Theme | Primary CTA |
| --- | --- | --- |
| 1 | Kindle launch / You are not finished | Amazon Kindle + Starter Kit |
| 2 | Foundation Inventory | Starter Kit |
| 3 | Compliance is not commitment | Tools |
| 4 | AI as strategic partner | AI ladder |
| 5 | Stabilize first | Scorecard |
| 6 | Ownership ladder | Tools |
| 7 | Title is not identity | Starter Kit |
| 8 | Three rings / reinvention intersection | Tools |
| 9 | Grief is not an event | Newsletter |
| 10 | Speaking/workshop positioning | Speaking inquiry |
| 11 | Tool walkthrough video | Tools |
| 12 | Sample chapter | Starter Kit |
| 13 | Reader/reviewer feedback ask | Book link |
| 14 | Launch recap / next chapter | Website |

# $500 Spend Guardrails

| Channel | Cap | Start condition | Stop condition |
| --- | --- | --- | --- |
| Meta lead magnet test | $150 | Starter Kit and Kit delivery verified | Pause if cost per subscriber is above $6 after $60 spend |
| LinkedIn boost | $75 | An organic post shows above-average engagement | Pause if click-through is below 0.8% after $40 spend |
| Amazon Ads | $100 | Amazon listing is live and detail page looks clean | Pause if no sales after $50 spend or CPC is materially above category economics |
| Creative/tool screenshots | $75 | Use only if needed for clean ad or social visuals | Spend only on reusable templates/assets |
| Reserve | $100 | Hold for the channel that shows traction | Do not spend until one channel has evidence |

Do not exceed $500 without explicit John approval. Do not scale any channel until the landing page, email capture, book CTA, and at least three creatives have been tested.

# Approval Gates

John approves the first launch email before send.

John approves any paid spend before activation.

John approves final paperback proof before paperback public launch.

John approves TestFlight/App Review submission after device UAT.

# Immediate Next Actions

Wait for KDP Kindle review result and live Amazon URL.

Wait for paperback proof delivery and physical review on or around 2026-06-13.

Keep website project files and tracking current.

Stage first launch email/social post with live-link placeholders.

Update website CTA and UAT script when the Amazon URL exists.

Continue TestFlight/device UAT and hardcover ISBN/setup prep when account access is available.